## Process Flow
CHATBOT PROCESS IDENTIFICATION
PHASES | ACTIVITIES | INPUTS | OUTPUTS | TOOLS & TECHNIQUES
Initiating | Industry Type | Discussions with Stake holders | Business Model( B2B or B2C) Features at High leve as stories Preferred decices ( Mobiles / desktops /both) Messaging Platforms to be used 1. Website 2. Skype 3. FB Messanger 4. Slack | Meetings/Emails
| Use Cases | Discussions with Stake holders | Use cases ( Personas, Conversation Flows) Setting a Purpose Picking a Bot Platform Defining Persona | Meetings/Emails
Planning | ChatBot Type-LUIS (Q&A, LUIS, Deep Learning) | Personas & Conversational Flows | Define ChatBot Type | Use cases
| Bot Builder(C#, Node.js) | Personas & Conversational Flows | Type of Bot Builder | Use cases
| List of Intents | Personas & Conversational Flows | Intents | Bot Framework
| List of Entities | Intents | Entities | Bot Framework
| List of utterences | Entities | Utterences | Bot Framework
| List of API's to be integrated | Intents,Entities,Utterences,Personas & Conversational Flows | API's | Node.js
| Channel for Publishing (Skype,Slack,Messenger,Email,FB,KIK) | Stake holder inputs | Channel | Selected Channel
Executing | Create Azure subscription | subscription detilas | Azure account to create a bot | Azure Portal
| Creating a Bot | MS Bot framework | Basic Bot | Bot Framework
| Train Intents,Entity and Utterences | List of Intents,Entities,utterences | Trained Bot | Bot Framework
| Integrate the API's | Api's List | Bot | Bot Framework
| Deploy the Bot | Bot |  | Bot Framework
| Connect to channel | Identified Channel | Availability of Bot on identified Channel | Selected Channel
Monitering and Controlling | Test the Bot | Bot | Modifications Required | Bot Framework
| Modify the bot source and re-deploy the Bot | Modifications | Modified Bot | Bot Framework
Closing | Publish the Bot | Modified Bot | Final Bot | Selected Channel
6500000
1000000
500000
500000
[6 empty] | 2000000 | 4500000

## Persona
How to define a persona ?
Name | SupportBot
Environment | Work
Audience | Adults aged 25-55, early adopters
Task at hand | Support Queries
Runtime variations | Record queries, Report absuse
Service Branding | Professional, Productive
Values | Getting things done and fast
Deried personality | Serios, to the point, friendly but not humoristic, safe for work.

## Conversation Scripting
How to script conversations of persona
Onboarding a new user
Main flow
Reguar Waterfall flow
Diamond Flow
Error Path Flow
Feedback Flow
Greetings
Define the purpose
Demo with Example
Call to Action
User
Initiates Action
Collect the Data
Verify the Data
Confirmation
Approval Process
Confirmation on Approval
Nofify User
Scheduled
User Initiated
Offer Recomendation
Prompt to Subscribe for more Recommendations
Error Path
User asks for Help
Offer Contextual Help
Prompt for Human Assistance
Loop in HR/Support/Admin Personnel
Carry on with Concersational Mode
End of Error Path
End of Success Path
User Initiated
Request for Measureable Quantitative Feedback
Request for Qualitative (Free Text) Feedback
Carry on with Concersational Mode